## MSc Project Gantt Chart
|  |  | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10
Phase | Task Number | Task | 2 Jun - 8 Jun | 9 Jun - 15 Jun | 16 Jun - 22 Jun | 23 Jun - 29 Jun | 30 Jun - 6 Jul | 7 Jul - 13 Jul | 14 Jul - 20 Jul | 21 Jul - 27 Jul | 28 Jul - 3 Aug | 4 Aug - 10 Aug
Research | 1 | Literature review | bar: Week1 to Week4
| 2 | Research Datasources | bar: Week1
| 3 | Researching Tools | bar: Week1
Design | 1 | System architecture | bar: Week2
| 2 | Database / Data-Pipeline design | bar: Week3
Develop | 1 | Initial project setup (MVC + FastAPI + Database) | bar: Week2
| 2 | Database Creation | bar: Week3
| 3 | ML model development | bar: Week4 to Week5
| 4 | FASTAPI Development | bar: Week4 to Week8
| 5 | Scenario Simulation Engine | bar: Week5 to Week6
| 6 | Frontend Views Development | bar: Week7 to Week8
| 7 | Prediction integration with Frontend | bar: Week8
| 8 | FrontEnd Dashboard | bar: Week9
| 9 | Bug Fixes | bar: Week9
Testing | 1 | System Testing | bar: Week8 to Week9
| 2 | Usability Testing | bar: Week10
Document | 1 | Intrioduction | bar: Week1
| 2 | Literature /Technology Review | bar: Week2 to Week4
| 3 | Implementation | bar: Week5 to Week7
| 4 | Evaluation and Results | bar: Week8 to Week9
| 5 | Conclusion and References | bar: Week9
| 6 | Finalize Report | bar: Week10
| 7 | Presentation Prep | bar: Week10